## Agile Project Roadmap
AGILE PROJECT ROADMAP TEMPLATE
Definiciones
AGO | SEPT | OCT | NOV | DEC
Fase 1
Fase 2
Fase 3
Despliegue Docker
Crear Base Datos
Creación Repositorios
Mockups
Presentación Final
Reunión de equipo
Reunión Dueño Local
Definición del proyecto
Determinación Equipo
Presentación del proyecto
Conexión BD
Desarrollo Python OCR
Módulo Alertas BD
Refinamiento de Modulos
Definición de tecnologías
Módulos Boletas y facturas
Dashboard Power BI
Módulos Boletas y facturas
Módulos Principal OCR
Refinamiento Modulos
Artefactos Sprint 1
Artefactos Sprint 2
Artefactos Sprint 3
Implementación Base
FRONTEND
BACKEND
Documentación
SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 0
Presentación Proyecto
SPRINT REFINAMIENTO
Análisis y requerimientos

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.